## Project Overview
GROUNDTRUTH — Zero-Hallucination Enterprise Knowledge Agent
Field | Details
Project Name | GroundTruth
Tagline | Zero-Hallucination Enterprise Knowledge Agent
Hackathon | Gemini Live Agent Challenge 2026
Category | Live Agents
Prize Target | Grand Prize ($25,000) + Best Live Agents ($10,000)
Deadline | March 16, 2026 — 5:00 PM PDT
Team Size | Solo
Status | In Development
TECH STACK
AI Model | Gemini 2.5 Flash (Native Audio) — Live API
SDK | Google GenAI SDK (google-genai v1.14+)
Backend | Python 3.11, FastAPI, WebSockets
Frontend | HTML5, Web Audio API, MediaDevices API
Deployment | Google Cloud Run, Docker
IaC | Terraform + gcloud CLI (bonus points)
Doc Processing | PyPDF2, python-docx
KEY DIFFERENTIATORS
Zero Hallucination | 5-layer grounding architecture ensures every response is cited
Multimodal | Voice (real-time) + Vision (camera) + Text input
Enterprise Security | Prompt injection defense, content treated as data not instructions
Audit Trail | Full transparency log of every query, citation, and validation
Citation Validation | Post-response checker verifies every [Source N] reference exists

## Execution Plan
48-HOUR EXECUTION PLAN
# | Task | Category | Priority | Est. Hours | Deadline | Status | Notes
1 | Set up Google Cloud account + billing | Setup | CRITICAL | 0.5 | Mar 14, 6:00 PM | Pending | Free $300 trial credits
2 | Create .env with Gemini API key | Setup | CRITICAL | 0.1 | Mar 14, 6:15 PM | Pending | Copy from .env.example
3 | Install Python dependencies | Setup | CRITICAL | 0.2 | Mar 14, 6:30 PM | Pending | pip install -r requirements.txt
4 | Test backend locally (python main.py) | Backend | CRITICAL | 0.5 | Mar 14, 7:00 PM | Pending | Verify http://localhost:8080
5 | Upload test documents + verify chunking | Backend | HIGH | 0.5 | Mar 14, 7:30 PM | Pending | Test PDF, DOCX, TXT
6 | Test text query endpoint with citations | Backend | HIGH | 0.5 | Mar 14, 8:00 PM | Pending | Verify [Source N] in responses
7 | Test WebSocket voice interaction | Frontend | HIGH | 1 | Mar 14, 9:00 PM | Pending | Hold mic, speak, hear response
8 | Test camera feed + vision integration | Frontend | HIGH | 1 | Mar 14, 10:00 PM | Pending | Point camera at document
9 | Fix bugs from testing | Debug | HIGH | 2 | Mar 15, 12:00 AM | Pending
10 | Hallucination resistance testing | QA | CRITICAL | 1 | Mar 15, 1:00 AM | Pending | Ask out-of-scope questions
11 | Polish frontend UI/UX | Frontend | MEDIUM | 1.5 | Mar 15, 3:00 AM | Pending | Animations, responsiveness
12 | Build Docker image + test locally | Deploy | HIGH | 1 | Mar 15, 10:00 AM | Pending | docker build && docker run
13 | Deploy to Google Cloud Run | Deploy | CRITICAL | 1 | Mar 15, 11:00 AM | Pending | Run deploy.sh
14 | Verify live deployment works | Deploy | CRITICAL | 0.5 | Mar 15, 12:00 PM | Pending | Test all 3 modalities live
15 | Render architecture diagram to PNG | Docs | HIGH | 0.3 | Mar 15, 1:00 PM | Pending | Use mermaid.live
16 | Screen record GCP deployment proof | Docs | HIGH | 0.3 | Mar 15, 1:30 PM | Pending | Show Cloud Run console
17 | Record demo video (4 min max) | Submission | CRITICAL | 2 | Mar 16, 10:00 AM | Pending | Follow DEMO_SCRIPT.md
18 | Edit and upload demo video | Submission | CRITICAL | 1 | Mar 16, 12:00 PM | Pending | YouTube unlisted
19 | Write + publish blog post | Bonus | MEDIUM | 1.5 | Mar 16, 1:30 PM | Pending | #GeminiLiveAgentChallenge
20 | Join Google Developer Group | Bonus | LOW | 0.1 | Mar 16, 2:00 PM | Pending | 2-minute task
21 | Push code to GitHub (public repo) | Submission | CRITICAL | 0.3 | Mar 16, 2:30 PM | Pending | Verify no API keys!
22 | Submit on DevPost | Submission | CRITICAL | 0.5 | Mar 16, 3:00 PM | Pending | Before 5 PM PDT!
23 | Final review of all submission items | Submission | CRITICAL | 0.5 | Mar 16, 4:00 PM | Pending | Double-check everything
|  |  | TOTAL HOURS: | 17.8

## Architecture
PROJECT ARCHITECTURE & FILE MAP
File Path | Component | Purpose | Lines (est.) | Complexity
backend/main.py | Backend | FastAPI server, WebSocket, REST endpoints, Gemini Live API | 280 | High
backend/document_store.py | Backend | Document ingestion, chunking, BM25 retrieval | 160 | Medium
backend/grounding_engine.py | Backend | Zero-hallucination pipeline, citation validation | 140 | High
backend/requirements.txt | Backend | Python dependencies | 12 | Low
backend/.env.example | Config | Environment variable template | 8 | Low
frontend/index.html | Frontend | Full UI: voice, camera, text, citations, audit trail | 650 | High
Dockerfile | Deploy | Multi-stage Docker build, non-root user, health check | 25 | Medium
deployment/deploy.sh | Deploy | One-command Cloud Run deployment script | 55 | Medium
deployment/terraform/main.tf | IaC | Terraform infrastructure-as-code for GCP | 90 | Medium
docs/architecture.mermaid | Docs | Full system architecture diagram | 60 | Low
docs/DEMO_SCRIPT.md | Docs | 4-minute demo video script with scenes | 100 | Low
docs/SUBMISSION_CHECKLIST.md | Docs | DevPost submission requirements tracker | 70 | Low
README.md | Docs | Complete project documentation | 120 | Low
.gitignore | Config | Git ignore rules | 10 | Low
|  | TOTAL LINES: | 1780

## Judging Scorecard
JUDGING CRITERIA ANALYSIS & SELF-ASSESSMENT
Criterion | Weight | Sub-Criteria | Our Approach | Self-Score (1-10) | Weighted Score
Innovation & Multimodal UX | 40% | Breaking beyond text paradigms | Voice + Vision + Text — full multimodal interaction | 9
|  | See/Hear/Speak integration | Gemini Live API: real-time audio + camera + text | 9
|  | Distinct persona/voice | Professional Kore voice + GroundTruth personality | 8
|  | Live & context-aware | Real-time streaming, document-grounded context | 9
|  | SUBTOTAL (avg) |  | 8.75 | 3.5
Technical Implementation | 30% | Effective GenAI SDK usage | google-genai SDK, Live API, proper session mgmt | 9
|  | Robust Cloud backend | Cloud Run, Docker, Terraform IaC | 8
|  | Sound agent logic | 5-layer grounding pipeline, BM25 retrieval | 9
|  | Hallucination avoidance | Citation enforcement + post-response validation | 10
|  | SUBTOTAL (avg) |  | 9 | 2.7
Demo & Presentation | 30% | Clear problem/solution | Enterprise hallucination problem — GroundTruth solution | 9
|  | Architecture diagram | Mermaid diagram with full pipeline visualization | 8
|  | Cloud deployment proof | deploy.sh recording + Cloud Run console | 8
|  | Live software demo | 4-min video: voice, camera, citations, hallucination test | 9
|  | SUBTOTAL (avg) |  | 8.5 | 2.55
PROJECTED TOTAL SCORE (out of 10) |  |  |  |  | 8.75

## Prize Analysis
PRIZE STRUCTURE & WIN PROBABILITY ANALYSIS
Prize Tier | Cash Prize | GCP Credits | Other Perks | Win Probability | Expected Value
Grand Prize (1 winner) | 25000 | 3000 | 2x Cloud Next tickets + travel ($6K), demo opportunity | 5% | 1250
Best Live Agents (1 winner) | 10000 | 1000 | 2x Cloud Next tickets, Google Coffee | 15% | 1500
Best Multimodal Integration (1) | 5000 | 500 | Google Coffee | 10% | 500
Best Technical Execution (1) | 5000 | 500 | Google Coffee | 12% | 600
Best Innovation & Thought Leadership (1) | 5000 | 500 | Google Coffee | 8% | 400
Honorable Mention (5 winners) | 2000 | 500 | Google Coffee | 20% | 400
|  |  |  | TOTAL EXPECTED VALUE: | 4650
Note: Prizes may be stackable (e.g., Grand Prize + Best Live Agents). Max potential: $35,000 + $4,000 GCP credits + conference perks.

## Submission Tracker
DEVPOST SUBMISSION REQUIREMENTS TRACKER
# | Requirement | Type | Status | Notes
1 | Text description (features, tech, learnings) | Required | Pending | Adapt from README.md
2 | Public GitHub repository | Required | Pending | Ensure no API keys in code
3 | Reproducible setup instructions in repo | Required | Pending | README has Quick Start section
4 | Google Cloud deployment proof (recording/code) | Required | Pending | Screen record deploy.sh running
5 | Architecture diagram (visual) | Required | Pending | Render architecture.mermaid to PNG
6 | Demo video (under 4 minutes) | Required | Pending | Follow DEMO_SCRIPT.md
7 | Live multimodal features shown (no mockups) | Required | Pending | Voice + Camera + Text in video
8 | Problem/solution pitch in video | Required | Pending | First 30 seconds of video
9 | Publish blog/content with #GeminiLiveAgentChallenge | Bonus | Pending | Medium or Dev.to post
10 | Automated Cloud deployment (IaC) | Bonus | Done | Terraform + deploy.sh included
11 | Join Google Developer Group (public profile) | Bonus | Pending | Takes 2 minutes
12 | Uses Gemini model | Universal Req | Done | gemini-2.5-flash-native-audio
13 | Uses Google GenAI SDK or ADK | Universal Req | Done | google-genai SDK
14 | Backend deployed on Google Cloud | Universal Req | Pending | Cloud Run deployment
15 | Includes at least one Google Cloud service | Universal Req | Pending | Cloud Run + (optional GCS)
|  | COMPLETION: | 3 / 15